## README
LA DIPERIE & LA FAYETTE — Resource Scheduler
YOUR BUSINESSES
La Diperie Oakville — Ice cream dip shop (established location)
La Diperie High Park — Ice cream dip shop (Toronto, shared space)
La Fayette — Coffee shop (shares High Park location with La Diperie HP)
WHAT THIS WORKBOOK DOES
Schedules your team of 7 across all 3 businesses over 16 weeks (Feb 23 → Jun 12).
Tracks who's working where, flags over-allocation when someone's stretched too thin,
and makes sure seasonal projects (menu launch, hiring) don't collide with daily ops.
⚠ SIMULATED DATA — Replace blue cells with your real numbers over time.
SETUP STEPS
1. SETTINGS — Confirm planning dates, hours/day, overtime rules.
2. RESOURCES — Verify team names, roles, availability, locations.
3. PROJECTS — Check the 7 projects reflect your current priorities.
4. TASKS — 29 tasks pre-loaded. Adjust hours and dates to match reality.
5. ASSIGNMENTS — This is the engine. Resource+Task+Week+Hours. All validations auto-run.
6. Review DEMAND_VS_CAPACITY for overloads and DASHBOARD for the big picture.
DEFINITIONS
Capacity: Max hours a person can work that week (max hrs × availability %).
Demand: Total hours assigned to them that week across all locations.
Utilization: Demand ÷ Capacity. You want 70-90%. Over 100% = someone's overbooked.
Over-allocation: Person assigned more hours than they're available for.
Unassigned work: Task hours not yet assigned to anyone — shows staffing gaps.
COLOR CODING
Blue text = Your editable inputs ¦ Green text = Auto-calculated formulas
Red highlight = Over-allocated / critical ¦ Yellow = Needs attention
Green highlight = Healthy / on-target ¦ Orange = Role/skill mismatch

## SETTINGS
SCHEDULING SETTINGS
Setting | Value | Unit/Notes
Planning Horizon Start | 2026-02-23 | Must be a Monday
Number of Weeks | 16 | weeks (covers through mid-June)
Working Days / Week | 7 | ice cream shops open 7 days
Standard Hours / Day | 8 | hours
Standard Hours / Week | 56 | auto-calculated (not used for staff — see Max Hrs/Wk)
Overtime Allowed | OFF | ON/OFF
Overtime Cap % | 20% | max extra % over max hours
Utilization Warning Threshold | 85% | flag above this
PLANNING WEEK CALENDAR |  |  | COLOR LEGEND
Week # | Week Starting | Week Ending | Green | On-target utilization (70-85%)
1 | 2026-02-23 | 2026-03-01 | Yellow | Warning — near capacity
2 | 2026-03-02 | 2026-03-08 | Red | Over-allocated — too many hours
3 | 2026-03-09 | 2026-03-15 | Orange | Role/skill mismatch
4 | 2026-03-16 | 2026-03-22 | Blue text | Editable input
5 | 2026-03-23 | 2026-03-29 | Green text | Formula / linked
6 | 2026-03-30 | 2026-04-05
7 | 2026-04-06 | 2026-04-12
8 | 2026-04-13 | 2026-04-19
9 | 2026-04-20 | 2026-04-26
10 | 2026-04-27 | 2026-05-03
11 | 2026-05-04 | 2026-05-10
12 | 2026-05-11 | 2026-05-17
13 | 2026-05-18 | 2026-05-24
14 | 2026-05-25 | 2026-05-31
15 | 2026-06-01 | 2026-06-07
16 | 2026-06-08 | 2026-06-14

## RESOURCES
Resource ID | Name | Role | Skill Tags | Location/Team | Cost/Hr ($) | Max Hrs/Week | Availability % | Notes
R001 | Anis Bouchema | Owner/Operator | Management,Scheduling,Ordering,Training,Inventory,Strategy | All Locations | 0 | 50 | 100% | Oversees all 3 businesses. Floats between locations.
R002 | Jess Moreau | Shift Lead | Dipping,Training,Opening/Closing,Cash,Inventory | La Diperie Oakville | 19 | 35 | 100% | Senior team member. Can train new hires.
R003 | Tyler Osei | Shift Lead | Barista,Dipping,Opening/Closing,Cash,Inventory | La Diperie HP / La Fayette | 19 | 35 | 100% | Runs HP location day-to-day. Cross-trained on coffee.
R004 | Maya Singh | Scooper/Barista | Dipping,Scooping,Cash,Customer Service | La Diperie Oakville | 17 | 25 | 100% | Part-time. Available evenings & weekends.
R005 | Ethan Tran | Scooper/Barista | Dipping,Scooping,Barista,Cash,Customer Service | La Diperie HP / La Fayette | 17 | 28 | 100% | Cross-trained ice cream + coffee. Reliable closer.
R006 | Olivia Brown | Scooper/Barista | Scooping,Dipping,Cash,Customer Service | La Diperie Oakville | 16.5 | 20 | 100% | Student. Weekends + some weeknights only.
R007 | Noah Lafleur | Barista | Barista,Latte Art,Cash,Customer Service | La Fayette | 17 | 25 | 80% | Coffee specialist. 80% avail (school schedule).

## PROJECTS
Project ID | Project Name | Priority | Start Date | End Date | Status | Owner | Notes
P001 | Spring/Summer Menu Launch | 1 | 2026-03-02 | 2026-05-01 | Planning | Anis Bouchema | New seasonal dip flavors, summer drinks, La Fayette iced menu. Biggest revenue driver.
P002 | Summer Hiring & Training | 1 | 2026-03-09 | 2026-05-15 | Planning | Anis Bouchema | Hire 2-3 new part-timers across locations. Train before May long weekend rush.
P003 | Daily Ops — La Diperie Oakville | 2 | 2026-02-23 | 2026-06-12 | In Progress | Jess Moreau | Ongoing shift coverage, opening/closing, inventory counts, cleaning.
P004 | Daily Ops — La Diperie High Park | 2 | 2026-02-23 | 2026-06-12 | In Progress | Tyler Osei | Ongoing shift coverage for HP ice cream side.
P005 | Daily Ops — La Fayette Coffee | 2 | 2026-02-23 | 2026-06-12 | In Progress | Tyler Osei | Ongoing coffee shop operations sharing HP space.
P006 | Inventory & Ordering Optimization | 3 | 2026-03-02 | 2026-04-17 | Planning | Anis Bouchema | Coordinate shared supplier orders, reduce waste, prep bulk buys for summer.
P007 | Social Media & Marketing Push | 3 | 2026-03-16 | 2026-05-29 | Not Started | Anis Bouchema | Spring launch content, local promos, La Fayette awareness campaign.

## TASKS
Task ID | Project ID | Task Name | Required Role | Required Skills | Start Date | End Date | Estimated Hours | Preferred Resource | Dependency | Notes
T001 | P001 | Test new dip flavors (R&D) | Owner/Operator | Management,Inventory | 2026-03-02 | 2026-03-20 | 12 | R001 |  | Sample from MTY + develop signature flavors
T002 | P001 | Design summer drinks menu (La Fayette) | Owner/Operator | Management,Strategy | 2026-03-09 | 2026-03-27 | 8 | R001 |  | Iced lattes, cold brew, smoothie combos
T003 | P001 | Order seasonal inventory & supplies | Owner/Operator | Ordering,Inventory | 2026-03-23 | 2026-04-03 | 6 | R001 | T001 | Place orders with Dubord, MTY, Monin etc.
T004 | P001 | Update POS menu & pricing | Shift Lead | Cash,Inventory | 2026-03-30 | 2026-04-10 | 8 | R002 | T001 | Program new items into both locations
T005 | P001 | Staff tasting & product training | Owner/Operator | Training | 2026-04-06 | 2026-04-17 | 6 | R001 | T003 | Train all staff on new products
T006 | P001 | Soft launch weekend (both locations) | Shift Lead | Dipping,Cash | 2026-04-20 | 2026-05-01 | 12 | R002 | T005 | Trial run before full launch
T007 | P002 | Write job postings & recruit | Owner/Operator | Management | 2026-03-09 | 2026-03-27 | 8 | R001 |  | Indeed, Instagram, walk-in applications
T008 | P002 | Interview candidates | Owner/Operator | Management | 2026-03-30 | 2026-04-10 | 10 | R001 | T007 | Screen 10-15, interview 6-8
T009 | P002 | Onboard new hires (paperwork, setup) | Owner/Operator | Management | 2026-04-13 | 2026-04-24 | 6 | R001 | T008
T010 | P002 | Shadow shifts — Oakville | Shift Lead | Training,Dipping | 2026-04-20 | 2026-05-08 | 15 | R002 | T009 | New hire trains with Jess
T011 | P002 | Shadow shifts — High Park / La Fayette | Shift Lead | Training,Barista,Dipping | 2026-04-20 | 2026-05-15 | 15 | R003 | T009 | New hire trains with Tyler
T012 | P003 | Weekly shift coverage — OAK | Shift Lead | Opening/Closing,Dipping,Cash | 2026-02-23 | 2026-06-12 | 240 | R002 |  | ~15h/wk ongoing. Core operating hours.
T013 | P003 | Inventory counts & restock — OAK | Shift Lead | Inventory | 2026-02-23 | 2026-06-12 | 48 | R002 |  | ~3h/wk, check pars, receive deliveries
T014 | P003 | Weekend/evening shifts — OAK | Scooper/Barista | Dipping,Scooping,Cash | 2026-02-23 | 2026-06-12 | 192 | R004 |  | ~12h/wk Maya
T015 | P003 | Weekend shifts — OAK (Olivia) | Scooper/Barista | Scooping,Dipping,Cash | 2026-02-23 | 2026-06-12 | 128 | R006 |  | ~8h/wk Olivia student schedule
T016 | P004 | Weekly shift coverage — HP | Shift Lead | Opening/Closing,Dipping,Cash | 2026-02-23 | 2026-06-12 | 240 | R003 |  | ~15h/wk Tyler runs HP
T017 | P004 | Inventory counts & restock — HP | Shift Lead | Inventory | 2026-02-23 | 2026-06-12 | 48 | R003 |  | ~3h/wk
T018 | P004 | Afternoon/evening shifts — HP | Scooper/Barista | Dipping,Cash,Customer Service | 2026-02-23 | 2026-06-12 | 168 | R005 |  | ~10.5h/wk Ethan on dip side
T019 | P005 | Morning coffee shifts — La Fayette | Barista | Barista,Cash | 2026-02-23 | 2026-06-12 | 160 | R007 |  | ~10h/wk Noah opens coffee side
T020 | P005 | Afternoon coffee coverage — La Fayette | Scooper/Barista | Barista,Cash | 2026-02-23 | 2026-06-12 | 112 | R005 |  | ~7h/wk Ethan covers afternoon coffee
T021 | P005 | Coffee inventory & supply orders | Shift Lead | Inventory,Barista | 2026-02-23 | 2026-06-12 | 32 | R003 |  | ~2h/wk Tyler handles coffee ordering too
T022 | P006 | Audit current pars & waste levels | Owner/Operator | Inventory,Management | 2026-03-02 | 2026-03-13 | 6 | R001 |  | Review both locations with new workbook
T023 | P006 | Set up shared bulk ordering schedule | Owner/Operator | Ordering,Inventory | 2026-03-16 | 2026-03-27 | 5 | R001 | T022 | Coordinate Dubord orders across locations
T024 | P006 | Pre-order summer stock (bulk buy) | Owner/Operator | Ordering,Inventory | 2026-03-30 | 2026-04-17 | 8 | R001 | T023 | Cones, toppings, packaging for peak season
T025 | P007 | Plan spring launch social content | Owner/Operator | Strategy | 2026-03-16 | 2026-03-27 | 5 | R001 |  | Instagram reels, stories, TikTok plan
T026 | P007 | Create & schedule posts (spring) | Shift Lead | Cash,Customer Service | 2026-03-30 | 2026-04-17 | 8 | R003 | T025 | Tyler handles HP/LaFayette socials
T027 | P007 | Local promo partnerships (Oakville) | Shift Lead | Cash,Customer Service | 2026-04-06 | 2026-05-01 | 6 | R002 |  | Jess connects with local businesses
T028 | P007 | La Fayette awareness campaign | Owner/Operator | Strategy,Management | 2026-04-13 | 2026-05-15 | 10 | R001 | T025 | Drive coffee traffic — separate from dip brand
T029 | P007 | Summer launch content blitz | Owner/Operator | Strategy | 2026-05-04 | 2026-05-29 | 8 | R001 |  | Ramp up posting for May long weekend + summer

## ASSIGNMENTS
Assignment ID | Task ID | Resource ID | Week Starting | Planned Hours | Status | Task Est Hrs | Assigned Total | Remaining | Role Match? | Date Range OK?
A001 | T001 | R001 | 2026-03-02 | 4 | Planned | 12 | 12 | 0 | OK | OK
A002 | T001 | R001 | 2026-03-09 | 4 | Planned | 12 | 12 | 0 | OK | OK
A003 | T001 | R001 | 2026-03-16 | 4 | Planned | 12 | 12 | 0 | OK | OK
A004 | T002 | R001 | 2026-03-09 | 2.7 | Planned | 8 | 8 | 0 | OK | OK
A005 | T002 | R001 | 2026-03-16 | 2.7 | Planned | 8 | 8 | 0 | OK | OK
A006 | T002 | R001 | 2026-03-23 | 2.6 | Planned | 8 | 8 | 0 | OK | OK
A007 | T003 | R001 | 2026-03-23 | 3 | Planned | 6 | 6 | 0 | OK | OK
A008 | T003 | R001 | 2026-03-30 | 3 | Planned | 6 | 6 | 0 | OK | OK
A009 | T004 | R002 | 2026-03-30 | 4 | Planned | 8 | 8 | 0 | OK | OK
A010 | T004 | R002 | 2026-04-06 | 4 | Planned | 8 | 8 | 0 | OK | OK
A011 | T005 | R001 | 2026-04-06 | 3 | Planned | 6 | 6 | 0 | OK | OK
A012 | T005 | R001 | 2026-04-13 | 3 | Planned | 6 | 6 | 0 | OK | OK
A013 | T006 | R002 | 2026-04-20 | 6 | Planned | 12 | 12 | 0 | OK | OK
A014 | T006 | R002 | 2026-04-27 | 6 | Planned | 12 | 12 | 0 | OK | OK
A015 | T007 | R001 | 2026-03-09 | 2.7 | Planned | 8 | 8 | 0 | OK | OK
A016 | T007 | R001 | 2026-03-16 | 2.7 | Planned | 8 | 8 | 0 | OK | OK
A017 | T007 | R001 | 2026-03-23 | 2.6 | Planned | 8 | 8 | 0 | OK | OK
A018 | T008 | R001 | 2026-03-30 | 5 | Planned | 10 | 10 | 0 | OK | OK
A019 | T008 | R001 | 2026-04-06 | 5 | Planned | 10 | 10 | 0 | OK | OK
A020 | T009 | R001 | 2026-04-13 | 3 | Planned | 6 | 6 | 0 | OK | OK
A021 | T009 | R001 | 2026-04-20 | 3 | Planned | 6 | 6 | 0 | OK | OK
A022 | T010 | R002 | 2026-04-20 | 5 | Planned | 15 | 15 | 0 | OK | OK
A023 | T010 | R002 | 2026-04-27 | 5 | Planned | 15 | 15 | 0 | OK | OK
A024 | T010 | R002 | 2026-05-04 | 5 | Planned | 15 | 15 | 0 | OK | OK
A025 | T011 | R003 | 2026-04-20 | 3.8 | Planned | 15 | 15 | 1.7764e-15 | OK | OK
A026 | T011 | R003 | 2026-04-27 | 3.8 | Planned | 15 | 15 | 1.7764e-15 | OK | OK
A027 | T011 | R003 | 2026-05-04 | 3.8 | Planned | 15 | 15 | 1.7764e-15 | OK | OK
A028 | T011 | R003 | 2026-05-11 | 3.6 | Planned | 15 | 15 | 1.7764e-15 | OK | OK
A029 | T012 | R002 | 2026-02-23 | 15 | In Progress | 240 | 240 | 0 | OK | OK
A030 | T012 | R002 | 2026-03-02 | 15 | Planned | 240 | 240 | 0 | OK | OK
A031 | T012 | R002 | 2026-03-09 | 15 | Planned | 240 | 240 | 0 | OK | OK
A032 | T012 | R002 | 2026-03-16 | 15 | Planned | 240 | 240 | 0 | OK | OK
A033 | T012 | R002 | 2026-03-23 | 15 | Planned | 240 | 240 | 0 | OK | OK
A034 | T012 | R002 | 2026-03-30 | 15 | Planned | 240 | 240 | 0 | OK | OK
A035 | T012 | R002 | 2026-04-06 | 15 | Planned | 240 | 240 | 0 | OK | OK
A036 | T012 | R002 | 2026-04-13 | 15 | Planned | 240 | 240 | 0 | OK | OK
A037 | T012 | R002 | 2026-04-20 | 15 | Planned | 240 | 240 | 0 | OK | OK
A038 | T012 | R002 | 2026-04-27 | 15 | Planned | 240 | 240 | 0 | OK | OK
A039 | T012 | R002 | 2026-05-04 | 15 | Planned | 240 | 240 | 0 | OK | OK
A040 | T012 | R002 | 2026-05-11 | 15 | Planned | 240 | 240 | 0 | OK | OK
A041 | T012 | R002 | 2026-05-18 | 15 | Planned | 240 | 240 | 0 | OK | OK
A042 | T012 | R002 | 2026-05-25 | 15 | Planned | 240 | 240 | 0 | OK | OK
A043 | T012 | R002 | 2026-06-01 | 15 | Planned | 240 | 240 | 0 | OK | OK
A044 | T012 | R002 | 2026-06-08 | 15 | Planned | 240 | 240 | 0 | OK | OK
A045 | T013 | R002 | 2026-02-23 | 3 | In Progress | 48 | 48 | 0 | OK | OK
A046 | T013 | R002 | 2026-03-02 | 3 | Planned | 48 | 48 | 0 | OK | OK
A047 | T013 | R002 | 2026-03-09 | 3 | Planned | 48 | 48 | 0 | OK | OK
A048 | T013 | R002 | 2026-03-16 | 3 | Planned | 48 | 48 | 0 | OK | OK
A049 | T013 | R002 | 2026-03-23 | 3 | Planned | 48 | 48 | 0 | OK | OK
A050 | T013 | R002 | 2026-03-30 | 3 | Planned | 48 | 48 | 0 | OK | OK
A051 | T013 | R002 | 2026-04-06 | 3 | Planned | 48 | 48 | 0 | OK | OK
A052 | T013 | R002 | 2026-04-13 | 3 | Planned | 48 | 48 | 0 | OK | OK
A053 | T013 | R002 | 2026-04-20 | 3 | Planned | 48 | 48 | 0 | OK | OK
A054 | T013 | R002 | 2026-04-27 | 3 | Planned | 48 | 48 | 0 | OK | OK
A055 | T013 | R002 | 2026-05-04 | 3 | Planned | 48 | 48 | 0 | OK | OK
A056 | T013 | R002 | 2026-05-11 | 3 | Planned | 48 | 48 | 0 | OK | OK
A057 | T013 | R002 | 2026-05-18 | 3 | Planned | 48 | 48 | 0 | OK | OK
A058 | T013 | R002 | 2026-05-25 | 3 | Planned | 48 | 48 | 0 | OK | OK
A059 | T013 | R002 | 2026-06-01 | 3 | Planned | 48 | 48 | 0 | OK | OK
A060 | T013 | R002 | 2026-06-08 | 3 | Planned | 48 | 48 | 0 | OK | OK
A061 | T014 | R004 | 2026-02-23 | 12 | In Progress | 192 | 192 | 0 | OK | OK
A062 | T014 | R004 | 2026-03-02 | 12 | Planned | 192 | 192 | 0 | OK | OK
A063 | T014 | R004 | 2026-03-09 | 12 | Planned | 192 | 192 | 0 | OK | OK
A064 | T014 | R004 | 2026-03-16 | 12 | Planned | 192 | 192 | 0 | OK | OK
A065 | T014 | R004 | 2026-03-23 | 12 | Planned | 192 | 192 | 0 | OK | OK
A066 | T014 | R004 | 2026-03-30 | 12 | Planned | 192 | 192 | 0 | OK | OK
A067 | T014 | R004 | 2026-04-06 | 12 | Planned | 192 | 192 | 0 | OK | OK
A068 | T014 | R004 | 2026-04-13 | 12 | Planned | 192 | 192 | 0 | OK | OK
A069 | T014 | R004 | 2026-04-20 | 12 | Planned | 192 | 192 | 0 | OK | OK
A070 | T014 | R004 | 2026-04-27 | 12 | Planned | 192 | 192 | 0 | OK | OK
A071 | T014 | R004 | 2026-05-04 | 12 | Planned | 192 | 192 | 0 | OK | OK
A072 | T014 | R004 | 2026-05-11 | 12 | Planned | 192 | 192 | 0 | OK | OK
A073 | T014 | R004 | 2026-05-18 | 12 | Planned | 192 | 192 | 0 | OK | OK
A074 | T014 | R004 | 2026-05-25 | 12 | Planned | 192 | 192 | 0 | OK | OK
A075 | T014 | R004 | 2026-06-01 | 12 | Planned | 192 | 192 | 0 | OK | OK
A076 | T014 | R004 | 2026-06-08 | 12 | Planned | 192 | 192 | 0 | OK | OK
A077 | T015 | R006 | 2026-02-23 | 8 | In Progress | 128 | 128 | 0 | OK | OK
A078 | T015 | R006 | 2026-03-02 | 8 | Planned | 128 | 128 | 0 | OK | OK
A079 | T015 | R006 | 2026-03-09 | 8 | Planned | 128 | 128 | 0 | OK | OK
A080 | T015 | R006 | 2026-03-16 | 8 | Planned | 128 | 128 | 0 | OK | OK
A081 | T015 | R006 | 2026-03-23 | 8 | Planned | 128 | 128 | 0 | OK | OK
A082 | T015 | R006 | 2026-03-30 | 8 | Planned | 128 | 128 | 0 | OK | OK
A083 | T015 | R006 | 2026-04-06 | 8 | Planned | 128 | 128 | 0 | OK | OK
A084 | T015 | R006 | 2026-04-13 | 8 | Planned | 128 | 128 | 0 | OK | OK
A085 | T015 | R006 | 2026-04-20 | 8 | Planned | 128 | 128 | 0 | OK | OK
A086 | T015 | R006 | 2026-04-27 | 8 | Planned | 128 | 128 | 0 | OK | OK
A087 | T015 | R006 | 2026-05-04 | 8 | Planned | 128 | 128 | 0 | OK | OK
A088 | T015 | R006 | 2026-05-11 | 8 | Planned | 128 | 128 | 0 | OK | OK
A089 | T015 | R006 | 2026-05-18 | 8 | Planned | 128 | 128 | 0 | OK | OK
A090 | T015 | R006 | 2026-05-25 | 8 | Planned | 128 | 128 | 0 | OK | OK
A091 | T015 | R006 | 2026-06-01 | 8 | Planned | 128 | 128 | 0 | OK | OK
A092 | T015 | R006 | 2026-06-08 | 8 | Planned | 128 | 128 | 0 | OK | OK
A093 | T016 | R003 | 2026-02-23 | 15 | In Progress | 240 | 240 | 0 | OK | OK
A094 | T016 | R003 | 2026-03-02 | 15 | Planned | 240 | 240 | 0 | OK | OK
A095 | T016 | R003 | 2026-03-09 | 15 | Planned | 240 | 240 | 0 | OK | OK
A096 | T016 | R003 | 2026-03-16 | 15 | Planned | 240 | 240 | 0 | OK | OK
A097 | T016 | R003 | 2026-03-23 | 15 | Planned | 240 | 240 | 0 | OK | OK
A098 | T016 | R003 | 2026-03-30 | 15 | Planned | 240 | 240 | 0 | OK | OK
A099 | T016 | R003 | 2026-04-06 | 15 | Planned | 240 | 240 | 0 | OK | OK
A100 | T016 | R003 | 2026-04-13 | 15 | Planned | 240 | 240 | 0 | OK | OK
A101 | T016 | R003 | 2026-04-20 | 15 | Planned | 240 | 240 | 0 | OK | OK
A102 | T016 | R003 | 2026-04-27 | 15 | Planned | 240 | 240 | 0 | OK | OK
A103 | T016 | R003 | 2026-05-04 | 15 | Planned | 240 | 240 | 0 | OK | OK
A104 | T016 | R003 | 2026-05-11 | 15 | Planned | 240 | 240 | 0 | OK | OK
A105 | T016 | R003 | 2026-05-18 | 15 | Planned | 240 | 240 | 0 | OK | OK
A106 | T016 | R003 | 2026-05-25 | 15 | Planned | 240 | 240 | 0 | OK | OK
A107 | T016 | R003 | 2026-06-01 | 15 | Planned | 240 | 240 | 0 | OK | OK
A108 | T016 | R003 | 2026-06-08 | 15 | Planned | 240 | 240 | 0 | OK | OK
A109 | T017 | R003 | 2026-02-23 | 3 | In Progress | 48 | 48 | 0 | OK | OK
A110 | T017 | R003 | 2026-03-02 | 3 | Planned | 48 | 48 | 0 | OK | OK
A111 | T017 | R003 | 2026-03-09 | 3 | Planned | 48 | 48 | 0 | OK | OK
A112 | T017 | R003 | 2026-03-16 | 3 | Planned | 48 | 48 | 0 | OK | OK
A113 | T017 | R003 | 2026-03-23 | 3 | Planned | 48 | 48 | 0 | OK | OK
A114 | T017 | R003 | 2026-03-30 | 3 | Planned | 48 | 48 | 0 | OK | OK
A115 | T017 | R003 | 2026-04-06 | 3 | Planned | 48 | 48 | 0 | OK | OK
A116 | T017 | R003 | 2026-04-13 | 3 | Planned | 48 | 48 | 0 | OK | OK
A117 | T017 | R003 | 2026-04-20 | 3 | Planned | 48 | 48 | 0 | OK | OK
A118 | T017 | R003 | 2026-04-27 | 3 | Planned | 48 | 48 | 0 | OK | OK
A119 | T017 | R003 | 2026-05-04 | 3 | Planned | 48 | 48 | 0 | OK | OK
A120 | T017 | R003 | 2026-05-11 | 3 | Planned | 48 | 48 | 0 | OK | OK
A121 | T017 | R003 | 2026-05-18 | 3 | Planned | 48 | 48 | 0 | OK | OK
A122 | T017 | R003 | 2026-05-25 | 3 | Planned | 48 | 48 | 0 | OK | OK
A123 | T017 | R003 | 2026-06-01 | 3 | Planned | 48 | 48 | 0 | OK | OK
A124 | T017 | R003 | 2026-06-08 | 3 | Planned | 48 | 48 | 0 | OK | OK
A125 | T018 | R005 | 2026-02-23 | 10.5 | In Progress | 168 | 168 | 0 | OK | OK
A126 | T018 | R005 | 2026-03-02 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A127 | T018 | R005 | 2026-03-09 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A128 | T018 | R005 | 2026-03-16 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A129 | T018 | R005 | 2026-03-23 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A130 | T018 | R005 | 2026-03-30 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A131 | T018 | R005 | 2026-04-06 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A132 | T018 | R005 | 2026-04-13 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A133 | T018 | R005 | 2026-04-20 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A134 | T018 | R005 | 2026-04-27 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A135 | T018 | R005 | 2026-05-04 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A136 | T018 | R005 | 2026-05-11 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A137 | T018 | R005 | 2026-05-18 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A138 | T018 | R005 | 2026-05-25 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A139 | T018 | R005 | 2026-06-01 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A140 | T018 | R005 | 2026-06-08 | 10.5 | Planned | 168 | 168 | 0 | OK | OK
A141 | T019 | R007 | 2026-02-23 | 10 | In Progress | 160 | 160 | 0 | OK | OK
A142 | T019 | R007 | 2026-03-02 | 10 | Planned | 160 | 160 | 0 | OK | OK
A143 | T019 | R007 | 2026-03-09 | 10 | Planned | 160 | 160 | 0 | OK | OK
A144 | T019 | R007 | 2026-03-16 | 10 | Planned | 160 | 160 | 0 | OK | OK
A145 | T019 | R007 | 2026-03-23 | 10 | Planned | 160 | 160 | 0 | OK | OK
A146 | T019 | R007 | 2026-03-30 | 10 | Planned | 160 | 160 | 0 | OK | OK
A147 | T019 | R007 | 2026-04-06 | 10 | Planned | 160 | 160 | 0 | OK | OK
A148 | T019 | R007 | 2026-04-13 | 10 | Planned | 160 | 160 | 0 | OK | OK
A149 | T019 | R007 | 2026-04-20 | 10 | Planned | 160 | 160 | 0 | OK | OK
A150 | T019 | R007 | 2026-04-27 | 10 | Planned | 160 | 160 | 0 | OK | OK
A151 | T019 | R007 | 2026-05-04 | 10 | Planned | 160 | 160 | 0 | OK | OK
A152 | T019 | R007 | 2026-05-11 | 10 | Planned | 160 | 160 | 0 | OK | OK
A153 | T019 | R007 | 2026-05-18 | 10 | Planned | 160 | 160 | 0 | OK | OK
A154 | T019 | R007 | 2026-05-25 | 10 | Planned | 160 | 160 | 0 | OK | OK
A155 | T019 | R007 | 2026-06-01 | 10 | Planned | 160 | 160 | 0 | OK | OK
A156 | T019 | R007 | 2026-06-08 | 10 | Planned | 160 | 160 | 0 | OK | OK
A157 | T020 | R005 | 2026-02-23 | 7 | In Progress | 112 | 112 | 0 | OK | OK
A158 | T020 | R005 | 2026-03-02 | 7 | Planned | 112 | 112 | 0 | OK | OK
A159 | T020 | R005 | 2026-03-09 | 7 | Planned | 112 | 112 | 0 | OK | OK
A160 | T020 | R005 | 2026-03-16 | 7 | Planned | 112 | 112 | 0 | OK | OK
A161 | T020 | R005 | 2026-03-23 | 7 | Planned | 112 | 112 | 0 | OK | OK
A162 | T020 | R005 | 2026-03-30 | 7 | Planned | 112 | 112 | 0 | OK | OK
A163 | T020 | R005 | 2026-04-06 | 7 | Planned | 112 | 112 | 0 | OK | OK
A164 | T020 | R005 | 2026-04-13 | 7 | Planned | 112 | 112 | 0 | OK | OK
A165 | T020 | R005 | 2026-04-20 | 7 | Planned | 112 | 112 | 0 | OK | OK
A166 | T020 | R005 | 2026-04-27 | 7 | Planned | 112 | 112 | 0 | OK | OK
A167 | T020 | R005 | 2026-05-04 | 7 | Planned | 112 | 112 | 0 | OK | OK
A168 | T020 | R005 | 2026-05-11 | 7 | Planned | 112 | 112 | 0 | OK | OK
A169 | T020 | R005 | 2026-05-18 | 7 | Planned | 112 | 112 | 0 | OK | OK
A170 | T020 | R005 | 2026-05-25 | 7 | Planned | 112 | 112 | 0 | OK | OK
A171 | T020 | R005 | 2026-06-01 | 7 | Planned | 112 | 112 | 0 | OK | OK
A172 | T020 | R005 | 2026-06-08 | 7 | Planned | 112 | 112 | 0 | OK | OK
A173 | T021 | R003 | 2026-02-23 | 2 | In Progress | 32 | 32 | 0 | OK | OK
A174 | T021 | R003 | 2026-03-02 | 2 | Planned | 32 | 32 | 0 | OK | OK
A175 | T021 | R003 | 2026-03-09 | 2 | Planned | 32 | 32 | 0 | OK | OK
A176 | T021 | R003 | 2026-03-16 | 2 | Planned | 32 | 32 | 0 | OK | OK
A177 | T021 | R003 | 2026-03-23 | 2 | Planned | 32 | 32 | 0 | OK | OK
A178 | T021 | R003 | 2026-03-30 | 2 | Planned | 32 | 32 | 0 | OK | OK
A179 | T021 | R003 | 2026-04-06 | 2 | Planned | 32 | 32 | 0 | OK | OK
A180 | T021 | R003 | 2026-04-13 | 2 | Planned | 32 | 32 | 0 | OK | OK
A181 | T021 | R003 | 2026-04-20 | 2 | Planned | 32 | 32 | 0 | OK | OK
A182 | T021 | R003 | 2026-04-27 | 2 | Planned | 32 | 32 | 0 | OK | OK
A183 | T021 | R003 | 2026-05-04 | 2 | Planned | 32 | 32 | 0 | OK | OK
A184 | T021 | R003 | 2026-05-11 | 2 | Planned | 32 | 32 | 0 | OK | OK
A185 | T021 | R003 | 2026-05-18 | 2 | Planned | 32 | 32 | 0 | OK | OK
A186 | T021 | R003 | 2026-05-25 | 2 | Planned | 32 | 32 | 0 | OK | OK
A187 | T021 | R003 | 2026-06-01 | 2 | Planned | 32 | 32 | 0 | OK | OK
A188 | T021 | R003 | 2026-06-08 | 2 | Planned | 32 | 32 | 0 | OK | OK
A189 | T022 | R001 | 2026-03-02 | 3 | Planned | 6 | 6 | 0 | OK | OK
A190 | T022 | R001 | 2026-03-09 | 3 | Planned | 6 | 6 | 0 | OK | OK
A191 | T023 | R001 | 2026-03-16 | 2.5 | Planned | 5 | 5 | 0 | OK | OK
A192 | T023 | R001 | 2026-03-23 | 2.5 | Planned | 5 | 5 | 0 | OK | OK
A193 | T024 | R001 | 2026-03-30 | 2.7 | Planned | 8 | 8 | 0 | OK | OK
A194 | T024 | R001 | 2026-04-06 | 2.7 | Planned | 8 | 8 | 0 | OK | OK
A195 | T024 | R001 | 2026-04-13 | 2.6 | Planned | 8 | 8 | 0 | OK | OK
A196 | T025 | R001 | 2026-03-16 | 2.5 | Planned | 5 | 5 | 0 | OK | OK
A197 | T025 | R001 | 2026-03-23 | 2.5 | Planned | 5 | 5 | 0 | OK | OK
A198 | T026 | R003 | 2026-03-30 | 2.7 | Planned | 8 | 8 | 0 | OK | OK
A199 | T026 | R003 | 2026-04-06 | 2.7 | Planned | 8 | 8 | 0 | OK | OK
A200 | T026 | R003 | 2026-04-13 | 2.6 | Planned | 8 | 8 | 0 | OK | OK
A201 | T027 | R002 | 2026-04-06 | 1.5 | Planned | 6 | 6 | 0 | OK | OK
A202 | T027 | R002 | 2026-04-13 | 1.5 | Planned | 6 | 6 | 0 | OK | OK
A203 | T027 | R002 | 2026-04-20 | 1.5 | Planned | 6 | 6 | 0 | OK | OK
A204 | T027 | R002 | 2026-04-27 | 1.5 | Planned | 6 | 6 | 0 | OK | OK
A205 | T028 | R001 | 2026-04-13 | 2 | Planned | 10 | 10 | 0 | OK | OK
A206 | T028 | R001 | 2026-04-20 | 2 | Planned | 10 | 10 | 0 | OK | OK
A207 | T028 | R001 | 2026-04-27 | 2 | Planned | 10 | 10 | 0 | OK | OK
A208 | T028 | R001 | 2026-05-04 | 2 | Planned | 10 | 10 | 0 | OK | OK
A209 | T028 | R001 | 2026-05-11 | 2 | Planned | 10 | 10 | 0 | OK | OK
A210 | T029 | R001 | 2026-05-04 | 2 | Planned | 8 | 8 | 0 | OK | OK
A211 | T029 | R001 | 2026-05-11 | 2 | Planned | 8 | 8 | 0 | OK | OK
A212 | T029 | R001 | 2026-05-18 | 2 | Planned | 8 | 8 | 0 | OK | OK
A213 | T029 | R001 | 2026-05-25 | 2 | Planned | 8 | 8 | 0 | OK | OK

## CAPACITY_MODEL
WEEKLY CAPACITY PER RESOURCE
Resource ID | Name | Role | Max Hrs/Wk | Avail % | 02/23 | 03/02 | 03/09 | 03/16 | 03/23 | 03/30 | 04/06 | 04/13 | 04/20 | 04/27 | 05/04 | 05/11 | 05/18 | 05/25 | 06/01 | 06/08
R001 | Anis Bouchema | Owner/Operator | 50 | 100% | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
R002 | Jess Moreau | Shift Lead | 35 | 100% | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
R003 | Tyler Osei | Shift Lead | 35 | 100% | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
R004 | Maya Singh | Scooper/Barista | 25 | 100% | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
R005 | Ethan Tran | Scooper/Barista | 28 | 100% | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
R006 | Olivia Brown | Scooper/Barista | 20 | 100% | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
R007 | Noah Lafleur | Barista | 25 | 80% | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
TIME OFF / EXCEPTIONS
Resource ID | Name | Start Date | End Date | Hours Reduction | Reason
R001 | Anis Bouchema | 2026-04-03 | 2026-04-05 | 16 | Good Friday/Easter weekend
R004 | Maya Singh | 2026-03-16 | 2026-03-22 | 25 | March Break — no availability
R007 | Noah Lafleur | 2026-04-06 | 2026-04-12 | 20 | School exams — reduced
R006 | Olivia Brown | 2026-04-20 | 2026-04-26 | 20 | Family trip
R003 | Tyler Osei | 2026-05-18 | 2026-05-22 | 35 | Vacation week

## DEMAND_VS_CAPACITY
DEMAND vs CAPACITY — PER RESOURCE PER WEEK
Week dates → |  |  | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08
DEMAND (Assigned Hours)
Resource ID | Name | Role | 02/23 | 03/02 | 03/09 | 03/16 | 03/23 | 03/30 | 04/06 | 04/13 | 04/20 | 04/27 | 05/04 | 05/11 | 05/18 | 05/25 | 06/01 | 06/08
R001 | Anis Bouchema | Owner/Operator | 0 | 7 | 12.4 | 14.4 | 13.2 | 10.7 | 10.7 | 10.6 | 5 | 2 | 4 | 4 | 2 | 2 | 0 | 0
R002 | Jess Moreau | Shift Lead | 18 | 18 | 18 | 18 | 18 | 22 | 23.5 | 19.5 | 30.5 | 30.5 | 23 | 18 | 18 | 18 | 18 | 18
R003 | Tyler Osei | Shift Lead | 20 | 20 | 20 | 20 | 20 | 22.7 | 22.7 | 22.6 | 23.8 | 23.8 | 23.8 | 23.6 | 20 | 20 | 20 | 20
R004 | Maya Singh | Scooper/Barista | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
R005 | Ethan Tran | Scooper/Barista | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5
R006 | Olivia Brown | Scooper/Barista | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
R007 | Noah Lafleur | Barista | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
CAPACITY (Available Hours)
Resource ID | Name | Role | 02/23 | 03/02 | 03/09 | 03/16 | 03/23 | 03/30 | 04/06 | 04/13 | 04/20 | 04/27 | 05/04 | 05/11 | 05/18 | 05/25 | 06/01 | 06/08
R001 | Anis Bouchema | Owner/Operator | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
R002 | Jess Moreau | Shift Lead | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
R003 | Tyler Osei | Shift Lead | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
R004 | Maya Singh | Scooper/Barista | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
R005 | Ethan Tran | Scooper/Barista | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
R006 | Olivia Brown | Scooper/Barista | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
R007 | Noah Lafleur | Barista | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
UTILIZATION %
Resource ID | Name | Role | 02/23 | 03/02 | 03/09 | 03/16 | 03/23 | 03/30 | 04/06 | 04/13 | 04/20 | 04/27 | 05/04 | 05/11 | 05/18 | 05/25 | 06/01 | 06/08
R001 | Anis Bouchema | Owner/Operator | 0% | 14% | 24.8% | 28.8% | 26.4% | 21.4% | 21.4% | 21.2% | 10% | 4% | 8% | 8% | 4% | 4% | 0% | 0%
R002 | Jess Moreau | Shift Lead | 51.43% | 51.43% | 51.43% | 51.43% | 51.43% | 62.86% | 67.14% | 55.71% | 87.14% | 87.14% | 65.71% | 51.43% | 51.43% | 51.43% | 51.43% | 51.43%
R003 | Tyler Osei | Shift Lead | 57.14% | 57.14% | 57.14% | 57.14% | 57.14% | 64.86% | 64.86% | 64.57% | 68% | 68% | 68% | 67.43% | 57.14% | 57.14% | 57.14% | 57.14%
R004 | Maya Singh | Scooper/Barista | 48% | 48% | 48% | 48% | 48% | 48% | 48% | 48% | 48% | 48% | 48% | 48% | 48% | 48% | 48% | 48%
R005 | Ethan Tran | Scooper/Barista | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5%
R006 | Olivia Brown | Scooper/Barista | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
R007 | Noah Lafleur | Barista | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
OVER-ALLOCATION FLAGS
Resource ID | Name | Role | 02/23 | 03/02 | 03/09 | 03/16 | 03/23 | 03/30 | 04/06 | 04/13 | 04/20 | 04/27 | 05/04 | 05/11 | 05/18 | 05/25 | 06/01 | 06/08
R001 | Anis Bouchema | Owner/Operator
R002 | Jess Moreau | Shift Lead
R003 | Tyler Osei | Shift Lead
R004 | Maya Singh | Scooper/Barista
R005 | Ethan Tran | Scooper/Barista
R006 | Olivia Brown | Scooper/Barista
R007 | Noah Lafleur | Barista

## SCHEDULE_VIEW
WEEKLY SCHEDULE VIEW
Shows total assigned hours per person per week. Red = over capacity.
|  |  | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08
Resource | Role | Location | 02/23 | 03/02 | 03/09 | 03/16 | 03/23 | 03/30 | 04/06 | 04/13 | 04/20 | 04/27 | 05/04 | 05/11 | 05/18 | 05/25 | 06/01 | 06/08
Anis Bouchema | Owner/Operator | All Locations | — | 7h | 12.4h | 14.4h | 13.2h | 10.7h | 10.7h | 10.6h | 5h | 2h | 4h | 4h | 2h | 2h | — | —
Jess Moreau | Shift Lead | La Diperie Oakville | 18h | 18h | 18h | 18h | 18h | 22h | 23.5h | 19.5h | 30.5h | 30.5h | 23h | 18h | 18h | 18h | 18h | 18h
Tyler Osei | Shift Lead | La Diperie HP / La Fayette | 20h | 20h | 20h | 20h | 20h | 22.7h | 22.7h | 22.6h | 23.8h | 23.8h | 23.8h | 23.6h | 20h | 20h | 20h | 20h
Maya Singh | Scooper/Barista | La Diperie Oakville | 12h | 12h | 12h | 12h | 12h | 12h | 12h | 12h | 12h | 12h | 12h | 12h | 12h | 12h | 12h | 12h
Ethan Tran | Scooper/Barista | La Diperie HP / La Fayette | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h | 17.5h
Olivia Brown | Scooper/Barista | La Diperie Oakville | bar: 2026-02-23 to 2026-06-08
Noah Lafleur | Barista | La Fayette | 10h | 10h | 10h | 10h | 10h | 10h | 10h | 10h | 10h | 10h | 10h | 10h | 10h | 10h | 10h | 10h

## PROJECT_VIEW
PROJECT STATUS VIEW
Project ID | Project Name | Priority | Status | Start | End | Total Est Hours | Assigned Hours | Remaining Hours | % Staffed | Risk Flag
P001 | Spring/Summer Menu Launch | 1 | Planning | 2026-03-02 | 2026-05-01 | 52 | 1530 | -1478 | 2942% | OK
P002 | Summer Hiring & Training | 1 | Planning | 2026-03-09 | 2026-05-15 | 54 | 0 | 54 | 0% | UNDERSTAFFED
P003 | Daily Ops — La Diperie Oakville | 2 | In Progress | 2026-02-23 | 2026-06-12 | 608 | 0 | 608 | 0% | UNDERSTAFFED
P004 | Daily Ops — La Diperie High Park | 2 | In Progress | 2026-02-23 | 2026-06-12 | 456 | 0 | 456 | 0% | UNDERSTAFFED
P005 | Daily Ops — La Fayette Coffee | 2 | In Progress | 2026-02-23 | 2026-06-12 | 304 | 0 | 304 | 0% | UNDERSTAFFED
P006 | Inventory & Ordering Optimization | 3 | Planning | 2026-03-02 | 2026-04-17 | 19 | 0 | 19 | 0% | UNDERSTAFFED
P007 | Social Media & Marketing Push | 3 | Not Started | 2026-03-16 | 2026-05-29 | 37 | 0 | 37 | 0% | UNDERSTAFFED

## DASHBOARD
LA DIPERIE & LA FAYETTE — SCHEDULING DASHBOARD
KPI | Value
Total Team Members | 7
Total Projects | 7
Total Tasks | 29
Total Estimated Hours (16 wks) | 1530
Total Assigned Hours | 1530
Unassigned Hours | 0
Over-Allocated Instances | 0
Projects at Risk | 6
Planning Horizon | Feb 23 → Jun 14, 2026
CAPACITY vs DEMAND BY WEEK
Metric | 02/23 | 03/02 | 03/09 | 03/16 | 03/23 | 03/30 | 04/06 | 04/13 | 04/20 | 04/27 | 05/04 | 05/11 | 05/18 | 05/25 | 06/01 | 06/08
Total Demand | 85.5 | 92.5 | 97.9 | 99.9 | 98.7 | 102.9 | 104.4 | 100.2 | 106.8 | 103.8 | 98.3 | 93.1 | 87.5 | 87.5 | 85.5 | 85.5
Total Capacity | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213
Avg Utilization | 40.14% | 43.43% | 45.96% | 46.9% | 46.34% | 48.31% | 49.01% | 47.04% | 50.14% | 48.73% | 46.15% | 43.71% | 41.08% | 41.08% | 40.14% | 40.14%
UTILIZATION BANDS (Week 1)
Band | # People
< 50% | 3
50–70% | 4
70–100% | 0
> 100% (OVER) | 0

## DATA_ISSUES
DATA QUALITY ISSUES
Issue # | Source Tab | Record ID | Issue Type | Details
1 | ASSIGNMENTS | A001
2 | ASSIGNMENTS | A002
3 | ASSIGNMENTS | A003
4 | ASSIGNMENTS | A004
5 | ASSIGNMENTS | A005
6 | ASSIGNMENTS | A006
7 | ASSIGNMENTS | A007
8 | ASSIGNMENTS | A008
9 | ASSIGNMENTS | A009
10 | ASSIGNMENTS | A010
11 | ASSIGNMENTS | A011
12 | ASSIGNMENTS | A012
13 | ASSIGNMENTS | A013
14 | ASSIGNMENTS | A014
15 | ASSIGNMENTS | A015
16 | ASSIGNMENTS | A016
17 | ASSIGNMENTS | A017
18 | ASSIGNMENTS | A018
19 | ASSIGNMENTS | A019
20 | ASSIGNMENTS | A020
21 | ASSIGNMENTS | A021
22 | ASSIGNMENTS | A022
23 | ASSIGNMENTS | A023
24 | ASSIGNMENTS | A024
25 | ASSIGNMENTS | A025 | Hours Gap | Task not fully assigned (0h remaining)
26 | ASSIGNMENTS | A026 | Hours Gap | Task not fully assigned (0h remaining)
27 | ASSIGNMENTS | A027 | Hours Gap | Task not fully assigned (0h remaining)
28 | ASSIGNMENTS | A028 | Hours Gap | Task not fully assigned (0h remaining)
29 | ASSIGNMENTS | A029
30 | ASSIGNMENTS | A030
31 | ASSIGNMENTS | A031
32 | ASSIGNMENTS | A032
33 | ASSIGNMENTS | A033
34 | ASSIGNMENTS | A034
35 | ASSIGNMENTS | A035
36 | ASSIGNMENTS | A036
37 | ASSIGNMENTS | A037
38 | ASSIGNMENTS | A038
39 | ASSIGNMENTS | A039
40 | ASSIGNMENTS | A040
41 | ASSIGNMENTS | A041
42 | ASSIGNMENTS | A042
43 | ASSIGNMENTS | A043
44 | ASSIGNMENTS | A044
45 | ASSIGNMENTS | A045
46 | ASSIGNMENTS | A046
47 | ASSIGNMENTS | A047
48 | ASSIGNMENTS | A048
49 | ASSIGNMENTS | A049
50 | ASSIGNMENTS | A050
51 | ASSIGNMENTS | A051
52 | ASSIGNMENTS | A052
53 | ASSIGNMENTS | A053
54 | ASSIGNMENTS | A054
55 | ASSIGNMENTS | A055
56 | ASSIGNMENTS | A056
57 | ASSIGNMENTS | A057
58 | ASSIGNMENTS | A058
59 | ASSIGNMENTS | A059
60 | ASSIGNMENTS | A060
61 | ASSIGNMENTS | A061
62 | ASSIGNMENTS | A062
63 | ASSIGNMENTS | A063
64 | ASSIGNMENTS | A064
65 | ASSIGNMENTS | A065
66 | ASSIGNMENTS | A066
67 | ASSIGNMENTS | A067
68 | ASSIGNMENTS | A068
69 | ASSIGNMENTS | A069
70 | ASSIGNMENTS | A070
71 | ASSIGNMENTS | A071
72 | ASSIGNMENTS | A072
73 | ASSIGNMENTS | A073
74 | ASSIGNMENTS | A074
75 | ASSIGNMENTS | A075
76 | ASSIGNMENTS | A076
77 | ASSIGNMENTS | A077
78 | ASSIGNMENTS | A078
79 | ASSIGNMENTS | A079
80 | ASSIGNMENTS | A080
81 | ASSIGNMENTS | A081
82 | ASSIGNMENTS | A082
83 | ASSIGNMENTS | A083
84 | ASSIGNMENTS | A084
85 | ASSIGNMENTS | A085
86 | ASSIGNMENTS | A086
87 | ASSIGNMENTS | A087
88 | ASSIGNMENTS | A088
89 | ASSIGNMENTS | A089
90 | ASSIGNMENTS | A090
91 | ASSIGNMENTS | A091
92 | ASSIGNMENTS | A092
93 | ASSIGNMENTS | A093
94 | ASSIGNMENTS | A094
95 | ASSIGNMENTS | A095
96 | ASSIGNMENTS | A096
97 | ASSIGNMENTS | A097
98 | ASSIGNMENTS | A098
99 | ASSIGNMENTS | A099
100 | ASSIGNMENTS | A100
101 | ASSIGNMENTS | A101
102 | ASSIGNMENTS | A102
103 | ASSIGNMENTS | A103
104 | ASSIGNMENTS | A104
105 | ASSIGNMENTS | A105
106 | ASSIGNMENTS | A106
107 | ASSIGNMENTS | A107
108 | ASSIGNMENTS | A108
109 | ASSIGNMENTS | A109
110 | ASSIGNMENTS | A110
111 | ASSIGNMENTS | A111
112 | ASSIGNMENTS | A112
113 | ASSIGNMENTS | A113
114 | ASSIGNMENTS | A114
115 | ASSIGNMENTS | A115
116 | ASSIGNMENTS | A116
117 | ASSIGNMENTS | A117
118 | ASSIGNMENTS | A118
119 | ASSIGNMENTS | A119
120 | ASSIGNMENTS | A120
121 | ASSIGNMENTS | A121
122 | ASSIGNMENTS | A122
123 | ASSIGNMENTS | A123
124 | ASSIGNMENTS | A124
125 | ASSIGNMENTS | A125
126 | ASSIGNMENTS | A126
127 | ASSIGNMENTS | A127
128 | ASSIGNMENTS | A128
129 | ASSIGNMENTS | A129
130 | ASSIGNMENTS | A130
131 | ASSIGNMENTS | A131
132 | ASSIGNMENTS | A132
133 | ASSIGNMENTS | A133
134 | ASSIGNMENTS | A134
135 | ASSIGNMENTS | A135
136 | ASSIGNMENTS | A136
137 | ASSIGNMENTS | A137
138 | ASSIGNMENTS | A138
139 | ASSIGNMENTS | A139
140 | ASSIGNMENTS | A140
141 | ASSIGNMENTS | A141
142 | ASSIGNMENTS | A142
143 | ASSIGNMENTS | A143
144 | ASSIGNMENTS | A144
145 | ASSIGNMENTS | A145
146 | ASSIGNMENTS | A146
147 | ASSIGNMENTS | A147
148 | ASSIGNMENTS | A148
149 | ASSIGNMENTS | A149
150 | ASSIGNMENTS | A150
151 | ASSIGNMENTS | A151
152 | ASSIGNMENTS | A152
153 | ASSIGNMENTS | A153
154 | ASSIGNMENTS | A154
155 | ASSIGNMENTS | A155
156 | ASSIGNMENTS | A156
157 | ASSIGNMENTS | A157
158 | ASSIGNMENTS | A158
159 | ASSIGNMENTS | A159
160 | ASSIGNMENTS | A160
161 | ASSIGNMENTS | A161
162 | ASSIGNMENTS | A162
163 | ASSIGNMENTS | A163
164 | ASSIGNMENTS | A164
165 | ASSIGNMENTS | A165
166 | ASSIGNMENTS | A166
167 | ASSIGNMENTS | A167
168 | ASSIGNMENTS | A168
169 | ASSIGNMENTS | A169
170 | ASSIGNMENTS | A170
171 | ASSIGNMENTS | A171
172 | ASSIGNMENTS | A172
173 | ASSIGNMENTS | A173
174 | ASSIGNMENTS | A174
175 | ASSIGNMENTS | A175
176 | ASSIGNMENTS | A176
177 | ASSIGNMENTS | A177
178 | ASSIGNMENTS | A178
179 | ASSIGNMENTS | A179
180 | ASSIGNMENTS | A180
181 | ASSIGNMENTS | A181
182 | ASSIGNMENTS | A182
183 | ASSIGNMENTS | A183
184 | ASSIGNMENTS | A184
185 | ASSIGNMENTS | A185
186 | ASSIGNMENTS | A186
187 | ASSIGNMENTS | A187
188 | ASSIGNMENTS | A188
189 | ASSIGNMENTS | A189
190 | ASSIGNMENTS | A190
191 | ASSIGNMENTS | A191
192 | ASSIGNMENTS | A192
193 | ASSIGNMENTS | A193
194 | ASSIGNMENTS | A194
195 | ASSIGNMENTS | A195
196 | ASSIGNMENTS | A196
197 | ASSIGNMENTS | A197
198 | ASSIGNMENTS | A198
199 | ASSIGNMENTS | A199
200 | ASSIGNMENTS | A200
201 | ASSIGNMENTS | A201
202 | ASSIGNMENTS | A202
203 | ASSIGNMENTS | A203
204 | ASSIGNMENTS | A204
205 | ASSIGNMENTS | A205
206 | ASSIGNMENTS | A206
207 | ASSIGNMENTS | A207
208 | ASSIGNMENTS | A208
209 | ASSIGNMENTS | A209
210 | ASSIGNMENTS | A210
211 | ASSIGNMENTS | A211
212 | ASSIGNMENTS | A212
213 | ASSIGNMENTS | A213